## Copy of Gantt Chart
GANTT CHART |  |  |  |  | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | AQ Testing |  |  | COMPANY NAME | [6 empty] | ECE 211
PROJECT MANAGER |  |  |  |  | DATE | [6 empty] | 2018-11-29
WBS NUMBER | TASK TITLE | DUE DATE | DONE? | ASSIGNED TO
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Planning
1.1 | Choose Project | 2018-11-27 | FALSE | GROUP | bar: WEEK 1 T; WEEK 3 R
1.2 | Assign Slides to each Team Member for Project Presentation | 2018-11-29 | FALSE | GROUP | bar: WEEK 1 R; WEEK 3 R
1.3 | Assign Parts to each Team Member for Project Report | 2018-11-29 | FALSE | GROUP | bar: WEEK 1 R; WEEK 3 R
1.4 | Finish and Turn in Project Presentation | 2018-12-05 | FALSE | GROUP | bar: WEEK 1 R; WEEK 3 R
1.5 | Finish and Turn in Project Report | 2018-12-06 | FALSE | GROUP | bar: WEEK 1 R; WEEK 3 R
1.6 | Order Project Components | 2018-12-12 | FALSE | GROUP | bar: WEEK 1 F; WEEK 3 R
2 | Prototype 1
2.1 | Construct Cardboard Shadow Box | 2018-10-25 | FALSE | JESSE | bar: WEEK 2 R; WEEK 3 R
2.2 | Connect and read data from Internet | 2018-10-25 | FALSE | CHUCK | bar: WEEK 2 R; WEEK 3 R
2.3 | Connect and Test LED Strips | 2018-10-25 | FALSE | EDGAR | bar: WEEK 2 R; WEEK 3 R
2.4 | Connect and Test Display | 2018-10-25 | FALSE | MATT | bar: WEEK 2 R; WEEK 3 R
2.5 | Create and Test Basic Code | 2018-10-30 | FALSE | GROUP | bar: WEEK 3 T; WEEK 3 R
2.6 | Test and Rework Full Construction | 2018-10-30 | FALSE | GROUP | bar: WEEK 3 T; WEEK 3 R
3 | Prototype 2
3.1 | Design Fancy Shadow Box | 2018-11-01 | FALSE | CHUCK/JESSE | bar: WEEK 3 R
3.1.1 | Construct Fancy Shadow Box | 2018-11-01 | FALSE | CHUCK/JESSE | bar: WEEK 3 R
3.2 | Figure out powering by rechargeable battery | 2018-11-01 | FALSE | bar: WEEK 3 R
3.3 | Connect and test LED strips | 2018-11-01 | FALSE | EDGAR | bar: WEEK 3 R
3.3.1 | Code LED strips to do cool things with photoresistor | 2018-11-01 | FALSE | EDGAR | bar: WEEK 3 R
3.4 | Connect and test different display | 2018-11-01 | FALSE | MATT | bar: WEEK 3 R
3.4.1 | Code and test display | 2018-11-01 | FALSE | MATT | bar: WEEK 3 R
3.5 | Create and Code Full Construction | 2018-11-02 | FALSE | GROUP | bar: WEEK 3 R to WEEK 3 F
3.5.1 | Test and Rework Full Construction | 2018-11-02 | FALSE | GROUP | bar: WEEK 3 R to WEEK 3 F
3.6 | Final Testing and Fine-Tuning | 2018-11-06 | FALSE | GROUP | bar: WEEK 3 R; WEEK 4 T
4 | Project Requirements
4.1 | Demo Practicum Project | 2018-11-08 | FALSE | GROUP | bar: WEEK 3 R; WEEK 4 R
4.2 | Write Retrospective Outline |  | FALSE | GROUP | bar: WEEK 3 R
4.2.1 | Write full Retrospective | 2018-11-20 | FALSE | bar: WEEK 3 R
4.3 | Brainstorm planned project for Wi19 |  | FALSE | GROUP | bar: WEEK 3 R
4.3.1 | Write outline of planned project for Wi19 |  | FALSE | GROUP | bar: WEEK 3 R
FALSE | bar: WEEK 3 R